## Sheet1
Week #1 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate | Actual Hours Taken |  | D1 | D2 | D3 | D4 | D5 | D6 | D7
[6 empty] | 2021-03-15 | 2021-03-16 | 2021-03-17 | 2021-03-18 | 2021-03-19 | 2021-03-20 | 2021-03-21
[5 empty] | Ideal Burndown | 40 | 31 | 22 | 13 | 4 | 0 | 0 | Ideal Burndown | Remaining Hours | Days of Sprint
|  |  | 40 | 24 | Remaining Hours | 10 | 9 | 4 | 0 | 0 | 0 | 0 | 40 | 10 | D1
Project Kick Start | Read and understand the project requirements individually | Bhavya Tetali | 5 | 3 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 31 | 9 | D2
| Read and understand the project requirements individually | Manjiri Kadam | 5 | 3 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 22 | 4 | D3
| Read and understand the project requirements individually | Pranjali Kotgire | 5 | 3 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | D4
| Read and understand the project requirements individually | Supriya Meduri | 5 | 3 |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | D5
Understanding the Project Requirements | Setup weekly scrum report | Bhavya Tetali | 5 | 3 |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | D6
| Research about the database requirements | Manjiri Kadam | 5 | 3 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | D7
| Requirement gathering on AWS components needed for the project | Pranjali Kotgire | 5 | 3 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0
| Requriement gathering on tech stack to choose | Supriya Meduri | 5 | 3 |  | 2 | 1 | 0 | 0 | 0 | 0 | 0
[6 empty] | Week #2 (10 hrs / week) | [6 empty] | Ideal Burndown | Remaining Hours | Days of Sprint
Backlog Item | Task | Task Owner | Initial Estimate | Actual Hours Taken |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | 40 | 7 | D8
[6 empty] | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-01 | 2021-04-02 | 2021-04-03 | 2021-04-04 | 31 | 7 | D9
[5 empty] | Ideal Burndown | 40 | 31 | 22 | 13 | 4 | -5 | 0 | 22 | 6 | D10
|  |  | 28 | 24 | Remaining Hours | 6 | 3 | 4 | 5 | 2 | 2 | 2 | 13 | 6 | D11
Planning Phase | Come up with the components involved in the project | Bhavya Tetali | 3 | 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | D12
| Come up with the database schema | Manjiri Kadam | 3 | 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | -5 | 3 | D13
| Come up with the AWS components required for the project | Pranjali Kotgire | 3 | 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | D14
| Come up with components involved in deployment | Supriya Meduri | 3 | 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0
Design Phase | Design Component Diagram | Bhavya Tetali | 4 | 4 |  | 1 | 1 | 0 | 1 | 1 | 0 | 0
| Design Entity Relationshp Diagram | Manjiri Kadam | 4 | 4 |  | 0 | 0 | 0 | 2 | 0 | 0 | 2
| Design Architecture Diagram | Pranjali Kotgire | 4 | 4 |  | 1 | 0 | 1 | 0 | 0 | 2 | 0
| Design Deployment Diagram | Supriya Meduri | 4 | 4 |  | 2 | 0 | 1 | 0 | 1 | 0 | 0
[13 empty] | Ideal Burndown | Remaining Hours | Days of Sprint
Backlog Item | Task | Task Owner | Initial Estimate | Actual Hours Taken |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | 40 | 8 | D9
[6 empty] | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 31 | 7 | D10
[5 empty] | Ideal Burndown | 40 | 31 | 22 | 13 | 4 | -5 | 0 | 22 | 7 | D11
|  |  | 40 | 36 | Remaining Hours | 7 | 7 | 6 | 6 | 7 | 3 | 0 | 13 | 6 | D12
Design Backend API's | Design Backend API for User Login and Signup | Bhavya Tetali | 7 | 6 |  | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 4 | 4 | D13
| Research about Backend API for One Time Account Transfer | Manjiri Kadam | 6 | 5 |  | 1 | 1 | 0 | 1 | 2 | 0 | 0 | -5 | 2 | D14
| Design Backend API for Add account | Pranjali Kotgire | 7 | 6 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | D15
| Design Backend API for Close Exsisting Accounts | Supriya Meduri | 7 | 6 |  | 2 | 0 | 2 | 0 | 2 | 0 | 0
Write Test cases for developed API's | Design Test Cases for User Login and Signup API's | Bhavya Tetali | 3 | 3 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0
| Research about Backend API for One Time Account Transfer | Manjiri Kadam | 4 | 4 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Design Test Cases for Add account Api's | Pranjali Kotgire | 3 | 3 |  | 0 | 0 | 0 | 1 | 1 | 1 | 0
| Design Test Cases for Close Exsisting Accounts Api | Supriya Meduri | 3 | 3 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0
[6 empty] | Week #4 (10 hrs / week) | [6 empty] | Ideal Burndown | Remaining Hours | Days of Sprint
Backlog Item | Task | Task Owner | Initial Estimate | Actual Hours Taken |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | 40 | 7 | D16
[6 empty] | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 31 | 8 | D17
[5 empty] | Ideal Burndown | 40 | 31 | 22 | 13 | 4 | -5 | 0 | 22 | 6 | D18
|  |  | 40 | 37 | Remaining Hours | 5 | 4 | 7 | 6 | 8 | 5 | 2 | 13 | 6 | D19
Design Backend API's | Design Backend API for View and Search Transactions | Bhavya Tetali | 7 | 6 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 4 | 5 | D20
| Research about Backend API for one time Account Transfer - external | Manjiri Kadam | 6 | 6 |  | 0 | 2 | 0 | 2 | 0 | 2 | 0 | -5 | 3 | D21
| Design Backend API for Add Transaction | Pranjali Kotgire | 7 | 6 |  | 1 | 0 | 2 | 0 | 2 | 0 | 1 | 0 | 0 | D22
| Research about Backend API for Recurring Transfer | Supriya Meduri | 7 | 6 |  | 2 | 0 | 2 | 0 | 2 | 0 | 0
Write Test cases for developed API's | Design Test Cases for View and Search Transactions API's | Bhavya Tetali | 3 | 3 |  | 0 | 0 | 0 | 1 | 1 | 1 | 0
| Research about Backend API for One Time bill payment | Manjiri Kadam | 4 | 4 |  | 1 | 0 | 1 | 0 | 1 | 0 | 1
| Design Test Cases for Add Transaction Api's | Pranjali Kotgire | 3 | 3 |  | 0 | 1 | 1 | 1 | 0 | 0 | 0
| Design Test Cases for Close Exsisting Accounts Api | Supriya Meduri | 3 | 3 |  | 0 | 0 | 0 | 1 | 1 | 1 | 0
[6 empty] | Week #5 (10 hrs / week) | [6 empty] | Ideal Burndown | Remaining Hours | Days of Sprint
Backlog Item | Task | Task Owner | Initial Estimate | Actual Hours Taken |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | 40 | 5 | D23
[6 empty] | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 31 | 5 | D24
[5 empty] | Ideal Burndown | 40 | 31 | 22 | 13 | 4 | -5 | 0 | 22 | 3 | D25
|  |  | 26 | 23 | Remaining Hours | 5 | 2 | 3 | 3 | 5 | 3 | 2 | 13 | 3 | D26
Create UI Wireframes/ Backend API's | Create UI Wireframes for all the front end pages | Bhavya Tetali | 5 | 4 |  | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 4 | 2 | D27
| Design Backend API for External Transfer | Manjiri Kadam | 8 | 7 |  | 2 | 0 | 1 | 0 | 1 | 1 | 2 | -5 | 2 | D28
| Create UI Wireframes for all the front end pages | Pranjali Kotgire | 5 | 5 |  | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | D29
| Design Backend API for Internal One Time Transfer | Supriya Meduri | 8 | 7 |  | 2 | 1 | 0 | 1 | 2 | 1 | 0
[6 empty] | Week #6 (10 hrs / week) | [6 empty] | Ideal Burndown | Remaining Hours | Days of Sprint
Backlog Item | Task | Task Owner | Initial Estimate | Actual Hours Taken |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | 40 | 5 | D30
[6 empty] | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 31 | 4 | D31
[5 empty] | Ideal Burndown | 40 | 31 | 22 | 13 | 4 | -5 | 0 | 22 | 3 | D32
|  |  | 27 | 20 | Remaining Hours | 5 | 4 | 3 | 3 | 2 | 1 | 0 | 13 | 2 | D33
Design UI/Backend API's | Research about UI | Bhavya Tetali | 5 | 3 |  | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 4 | 1 | D34
| Design Backend API for One Time bill Payment | Manjiri Kadam | 8 | 6 |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | -5 | 0 | D35
| Update Backend API for Add Transaction | Pranjali Kotgire | 8 | 6 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | D36
| Design Test Cases for Internal One Time Transfer Api | Supriya Meduri | 6 | 5 |  | 1 | 0 | 0 | 2 | 0 | 0 | 0
[6 empty] | Week #7 (10 hrs / week) | [6 empty] | Ideal Burndown | Remaining Hours | Days of Sprint
Backlog Item | Task | Task Owner | Initial Estimate | Actual Hours Taken |  | D1 | D2 | D3 | D4 | D5 | D6 | D7 | 40 | 7 | D37
[6 empty] | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 31 | 7 | D38
[5 empty] | Ideal Burndown | 40 | 31 | 22 | 13 | 4 | -5 | 0 | 22 | 4 | D39
|  |  | 40 | 32 | Remaining Hours | 7 | 3 | 5 | 4 | 4 | 4 | 2 | 13 | 4 | D40
Create Front End Pages | Create front end pages for Login/Signup and Dashboard | Bhavya Tetali | 6 | 5 |  | 2 | 0 | 0 | 0 | 1 | 1 | 1 | 4 | 3 | D41
| Create Backend API for Backend Bill Payment API | Manjiri Kadam | 6 | 5 |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | -5 | 3 | D42
| Create front end pages for Add Account | Pranjali Kotgire | 6 | 5 |  | 2 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | D43
| Create front end page for Close Account | Supriya Meduri | 6 | 5 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Create front end pages for View and Search transaction | Bhavya Tetali | 4 | 3 |  | 0 | 1 | 0 | 1 | 0 | 1 | 0
| Create front end pages for External Transfer and One time Bill Payment | Manjiri Kadam | 4 | 3 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0
| Create front end pages for add manual transaction | Pranjali Kotgire | 4 | 3 |  | 0 | 0 | 0 | 1 | 1 | 1 | 0
| Create front end page for Internal transfer between accounts | Supriya Meduri | 4 | 3 |  | 2 | 1 | 0 | 0 | 0 | 0 | 0
[6 empty] | Week #8 (10 hrs / week) | [6 empty] | Ideal Burndown | Remaining Hours | Days of Sprint
Backlog Item | Task | Task Owner | Initial Estimate | Actual Hours Taken |  | D1 | D2 | D3 | D4 |  |  |  | 40 | 9 | D44
[6 empty] | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 |  |  |  | 31 | 8 | D45
[5 empty] | Ideal Burndown | 40 | 31 | 22 | 13 |  |  |  | 22 | 6 | D46
|  |  | 40 | 28 | Remaining Hours | 9 | 8 | 6 | 5 |  |  |  | 13 | 5 | D47
Deployment/Documentation | Create View and Search UI for Admin Dashboard | Bhavya Tetali | 7 | 5 |  | 3 | 1 | 1 | 0
| Create Backend for Recurring Transfer,Recurring Bill Payment | Manjiri Kadam | 6 | 6 |  | 1 | 2 | 1 | 2
| Work on Project Presentation | Pranjali Kotgire | 3 | 1 |  | 0 | 0 | 0 | 1
| Work on Burndown Chart | Supriya Meduri | 3 | 2 |  | 0 | 0 | 1 | 1
| Create ReadMe file for the project | Bhavya Tetali | 3 | 2 |  | 0 | 0 | 1 | 1
| Create Frontend for Recurring Transfer,Recurring Bill Payment | Manjiri Kadam | 4 | 4 |  | 1 | 1 | 2 | 0
| Work on hosting application in AWS EC2 instances | Pranjali Kotgire | 7 | 4 |  | 2 | 2 | 0 | 0
| Work on setting up AWS components for deployment | Supriya Meduri | 7 | 4 |  | 2 | 2 | 0
Team:
Bhavya Tetali | 10 hours / Week
Manjiri Kadam | 10 hours / Week
Pranjali Kotgire | 10 hours / Week
Supriya Meduri | 10 hours / Week
Total Available Hours During Sprint: | 40 x 9 = 360 Hours
XP Value carried Throughout the Project | COMMUNICATION